## Slide 1
Booking Management System
Software Engineering Project
Dhurba Tripathi (dt2202)
Yi Wang (yw4549)
Presented To:
Professor Mai Oudah

## Slide 2
Need for the system
System Modelling
Communication and Planning
03
05
02
Content
01
04
Implementation and Testing
Demo

## Slide 3
The need for an online booking system
Traditional methods of booking: phone calls, emails - very tedious (Problem of: No show)
Online booking - user convenience and customer satisfaction
Attract more climbers/ climbing enthusiasts by utilizing internet technology and publicity

## Slide 4
Communication and Planning
Requirement gathering
Economic feasibility
Project size
Work plan
Modeling
Use case diagram
Class diagram
Activity diagram
Sequence diagram
Implementation and testing
Design test cases
Implement a demo
Test the demo

## Slide 5
01
Communication and planning
Requirement gathering
Economic feasibility
Project size
Work Plan

## Slide 6
Interview
Motivation
Q1: Why do you need a online booking system?
-It’s much more convenient than booking by calls.(3)
-It saves our money as phone calls are not free.(1)
Basic Functions
Q2: Is it fine for you that you will be warned of not showing?
-Yes.(0)
-No.(3) Make us pay in advance will solve the problem.
Q3: What do you want us to do if the date and time you want to book is full?
-Nothing.(1)
-Add us to waitlist and inform us once someone cancels the booking.(2)
Q4: Is it fine for you that you will receive automatic emails once the order is completed?
-Yes.(3)
-No.(0)
Supplement Functions
Q5: Any functions apart from basic ones you want to add? (describe those already in mind)
-Book a coach. Additional fees or membership only.
-It’s annoying to explain what I need every time. Can you add a function that I can just input the requirements and then they will know.
-Can you use the nfc technique to mark the routes and I can check them with my phone?
Requirement Gathering

## Slide 7
Create a user account
Make a booking
1
2
3
4
SRS Summary
5
Admin login
Coach login
Sign up for membership
1. Login to the system with two factor authentication
2. View all bookings
3. Manage coach accounts
1. Login to the system
2. View the timings for which they are booked
3. Mark available timings
4. View the hours of past sessions coached
1. Select membership type
2. Promo codes for discounts
3. Payment
4. Confirmation message
1. Login to the system
2. Pick a date and time
3. Book a coach
4. Stay in waitlist if currently not available.
1. Information form
2. Error checking
3. Verification code via Email

## Slide 8
Economic Feasibility
Costs | Period1 | Period2 | Period3 | Period4 | Period5 | Period6 | Total
Salaries | 20 | 20 | 20 | 20 | 0 | 0 | 80
H/W & S/W | 20 | 0 | 0 | 0 | 0 | 0 | 20
Training | 30 | 0 | 0 | 0 | 0 | 0 | 30
Support and Maintenance | 0 | 0 | 0 | 0 | 10 | 10 | 20
Total costs | 70 | 20 | 20 | 20 | 10 | 10 | 150
Benefits |  |  |  |  |  |  | 
Increase # of customers | 0 | 0 | 0 | 0 | 300 | 300 | 600
Decrease costs | 0 | 0 | 0 | 0 | 30 | 30 | 60
Total Benefits | 0 | 0 | 0 | 0 | 330 | 330 | 660
NCF | (70) | (20) | (20) | (20) | 320 | 320 | 510
CNCF | (70) | (90) | (110) | (130) | 190 | 510 | 1020
Numbers are in thousands of DHS
NCF: Net Cash Flow
CNCF: Cumulative Net Cash Flow
One period corresponds to two weeks
H/w and S/w correspond to Hardware and Software respectively

## Slide 9
Economic Feasibility
The return on investment (ROI):
ROI = (Total Benefits - Total Costs) / Total Costs
= (660-150)/150
=340 %
The break-even point (BEP):
BEP = (Period.net cash flow - Cumulative.net cash flow) / Period.net cash flow
= (320-190)/190 = 68%
= 0.68*1*14 =9.50 ≈ 10 days
So the Project will take 8 weeks and 10 days which is 56 days.
Conclusion:
The ROI is good for this booking system, and the BEP is only a bit greater than the reality.
So the risk is relatively low.

## Slide 10
Project Size
Functionality | Input | Output | Queries | File | Interface
Registration | 3 | 2 | 1 | 1 | 0
Login | 2 | 1 | 1 | 1 | 0
Booking | 1 | 1 | 1 | 1 | 0
Payment | 1 | 1 | 1 | 1 | 1
Membership | 1 | 1 | 1 | 1 | 0
Notification | 0 | 1 | 3 | 1 | 0
Information domains | Count | Weighting Factor |  |  | Total
 |  | Simple | Average | Complex | 
EIs | 8 | 4*3 | 3*4 | 1*6 | 30
EOs | 7 | 4*4 | 3*5 | 0*7 | 31
EQs | 8 | 2*3 | 3*4 | 3*6 | 36
ILFs | 6 | 2*7 | 4*10 | 0*15 | 54
EIFs | 1 | 0*5 | 1*7 | 0*10 | 7
Total Unadjusted Function Points (TUFP) = |  |  |  |  | 158
Function Point Estimation

## Slide 11
Project Size
The total processing complexity (PC)
Tasks | Complexity
Familiarity with technology | 2
Online data entry | 2
​​Data communication | 3
Transaction rate | 2
Multiple sites | 2
Performance | 3
Operating ease | 2
Total Processing Complexity (TPC) = | 16
*Complexity is from 0 to 3: (0 = no effect on project complexity; 3 = great effect on project complexity)
The adjusted processing complexity (APC)
APC = 0.65 + (0.01 * TPC)
APC = 0.65 + (0.01 * 16) = 0.81
The total adjusted function points (TAFP)
TAFP = TUFP * APC = 158 * 0.81 = 127.98
Converting Function Points to Line Of Code (LOC)
• 70% will be done in Javascript
• 30% will be done in HTML and CSS (for layouts only)
Number of lines of code (LOC) = TAFP * # of (LOC\FP) * %
For Javascript = (127.98) *(71.11)*(70/100) = 6370.46 LOC
For HTML/CSS = (127.98) *(15)*(30/100) = 575.91 LOC
So the total LOC = 6946.37 LOC = 6.95 KLOC
Estimating the effort
Effort
= 2.4 * KLOC1.05
= 2.4 * 6.951.05
= 18.38
Estimating the schedule time
Time
= 2.5 * (effort)0.38
= 2.5 * (18.38)0.38 = 7.55
Estimating the number of persons
average of # of persons
= effort/time
= 18.38 / 7.55 = 2.43 persons

## Slide 12
Work Plan (Gantt Chart)

## Slide 13
Lack of Technical Experts and small team size
Time constrainsts
Semi-familiarity with technologies to use.
Scale of the project is underestimated
Risk Analysis
Lack of free training / funding, for required skills is unavailable

## Slide 14
02
System Modelling
Use case diagram
Class diagram
Activity diagram
Sequence diagram

## Slide 15
Use Case Diagram

## Slide 16
Class Diagram

## Slide 17
Activity Diagrams

## Slide 18
Sequence Diagrams

## Slide 19
03
Implementation and Testing
Design test cases
Implement a demo
Test the demo

## Slide 20
Html, Css,
Javascript, ReactJs
Firebase
Technologies
Google Firebase Authentication
Authentication
Google Firebase Realtime Databse
Database
Implementation

## Slide 21
Testing
Test cases | Priority | Bug step | Solution
1. Make a non-membership booking (available). | High | No bugs | Success
2. Make a non-membership booking (not available). | Medium | No bugs | Success
4. Notify those in a waitlist of a new slot. | Medium | Failure | Yet to implement
5. Make a coach booking | High | No bugs | Success
6. Cancel a booking | High | No bugs | Success
7. Create a new account | High | No bugs | Success
8. Sign up for membership | High | Failure | Yet to implement
9. User login and logout | High | No bugs | Success
10. Operations for coach | Medium | Failure | Yet to implement
11. Operations for admin | Medium | Failure | Yet to implement

## Slide 22
04
DEMO

## Slide 23
Thanks for watching !